## Issue Log
Issue ID | Scope | Problem | Source 1 | Source 2 | Control Direction | Finding | Decision | Old Value | New Value | Action | Validation | Status | Notes
ISS-001 | All Order IDs | Number format used for Unit Price | RAW_Orders | Unit_Price_TRY | RAW_Orders -> Unit_Price_TRY | Format Error | Currency format should be used. | None | None | Data type standardized in the clean table. | Data type check during clean-table preparation. | Corrected
ISS-002 | All Order IDs | General format used for Order ID | RAW_Orders | Order_ID | RAW_Orders -> Order_ID | Format Error | Order IDs should be stored as text identifiers. | None | None | Identifier format standardized in the clean table. | Data type check during clean-table preparation. | Corrected
ISS-003 | All Customer IDs | General format used for Customer ID | RAW_Orders | Customer_ID | RAW_Orders -> Customer_ID | Format Error | Customer IDs should be stored as text identifiers. | None | None | Identifier format standardized in the clean table. | Data type check during clean-table preparation. | Corrected
ISS-004 | All Customer IDs | General format used for Customer ID | RAW_Customers | Customer_ID | RAW_Customers -> Customer_ID | Format Error | Customer IDs should be stored as text identifiers. | None | None | Identifier format standardized in the clean table. | Data type check during clean-table preparation. | Corrected
ISS-005 | All Product IDs | General format used for Product ID | RAW_Orders | Product_ID | RAW_Orders -> Product_ID | Format Error | Product IDs should be stored as text identifiers. | None | None | Identifier format standardized in the clean table. | Data type check during clean-table preparation. | Corrected
ISS-006 | All Status values | Inconsistent text casing | RAW_Orders | Status | RAW_Orders -> Status | Data Error | Status values used inconsistent casing (e.g. Completed/completed). | Completed, completed | None | Status values standardized. | Standardization check. | Corrected
ISS-007 | All Customer IDs | Inconsistent identifier casing | RAW_Orders | Customer_ID | RAW_Orders -> Customer_ID | Data Error | Customer ID dc002 used inconsistent casing. | dc002 | None | Customer ID standardized. | Cross-table consistency check. | Corrected
ISS-008 | All Customer IDs | Inconsistent identifier casing | RAW_Customers | Customer_ID | RAW_Customers -> Customer_ID | Data Error | Customer ID dc002 used inconsistent casing. | dc002 | None | Customer ID standardized. | Cross-table consistency check. | Corrected
ISS-009 | All Status values | Manual entry control | RAW_Orders | Status | RAW_Orders -> Status | Data Entry Check | Status field required controlled input. | None | None | Dropdown validation added in the working dataset. | Standardization control. | Corrected
ISS-010 | All Quantity values | General format used for Quantity | RAW_Orders | Quantity | RAW_Orders -> Quantity | Format Error | Quantity should be a positive integer. | None | None | Quantity type standardized in the clean table. | Data type check. | Corrected
ISS-011 | Problem record 0100101 | Duplicate customer/order records identified | RAW_Orders | RAW_Customers | RAW_Orders -> RAW_Customers | Duplicate Record | Duplicate Customer_ID and Order_ID records were identified. | Duplicate records | None | Duplicate records removed. | Duplicate removal check. | Corrected
ISS-012 | C0012; C0020; C0028; C0261; C0318; C0328; C0467; C0525; C0574 | Nine customer IDs are present in Customers but not used by Orders. | RAW_Orders | RAW_Customers | RAW_Orders -> RAW_Customers | Unmatched Customer IDs | The IDs exist in Customers but there is no confirmed order record for them. | Nine IDs | No change | No order records added; no independent source was available. | Manual relationship check. | Closed - No Action Required | These may represent customers with no orders; no evidence justified synthetic orders.
ISS-013 | O101101 | Order has no Unit Price | RAW_Orders | Unit_Price_TRY | RAW_Orders -> Unit_Price_TRY | Missing Unit Price | The order has a missing Unit Price. | None | None | No imputation or deletion performed. | Source validation required. | Closed - No Action Required | Product Unit Cost was not substituted for sales price.
ISS-014 | O101501 | Invalid Order Date | RAW_Orders | Order_Date | RAW_Orders -> Order_Date | Invalid Order Date | Order Date is written as 2026/04/31, which is not a valid date. | 2026/04/31 | None | Original value preserved; excluded from monthly grouping. | Source validation required. | Closed - No Action Required | Monthly analysis excludes this row from month-level aggregation.
ISS-015 | O101851 | Quantity entered as text | RAW_Orders | Quantity | RAW_Orders -> Quantity | Text Quantity | Quantity was entered as the word 'two'. | two | 2 | Numeric quantity standardized in clean data. | Quantity validation. | Corrected
ISS-016 | O101301 | Negative Quantity detected | RAW_Orders | Quantity | RAW_Orders -> Quantity | Negative Quantity | Quantity was entered as -2 in the raw source. | -2 | 2 | Final clean table uses a positive numeric quantity; original issue remains documented. | Quantity validation. | Corrected
ISS-017 | All Product IDs | General format used for Product ID | Raw Products | Product_ID | Raw Products -> Product_ID | Format Error | Product IDs should be stored as text identifiers. | None | None | Identifier format standardized in the clean table. | Data type check. | Corrected
ISS-018 | All Categories | Manual entry control | Raw Products | Category | Raw Products -> Category | Data Entry Check | Category values should use controlled input. | None | None | Controlled category selection added in the working dataset. | Standardization control. | Corrected
ISS-019 | All Suppliers | Manual entry control | Raw Products | Supplier | Raw Products -> Supplier | Data Entry Check | Supplier values should use controlled input. | None | None | Controlled supplier selection added in the working dataset. | Standardization control. | Corrected
ISS-020 | All Unit Costs | General format used for Unit Cost | Raw Products | Unit_Cost_TRY | Raw Products -> Unit_Cost_TRY | Format Error | Unit Cost should use currency formatting. | None | None | Currency format standardized in the clean table. | Data type check. | Corrected
ISS-021 | All Return IDs | General format used for Return ID | Raw Returns | Return_ID | Raw Returns -> Return_ID | Format Error | Return IDs should be stored as text identifiers. | None | None | Identifier format standardized in the clean table. | Data type check. | Corrected
ISS-022 | All Order IDs | General format used for Return Order ID | Raw Returns | Order_ID | Raw Returns -> Order_ID | Format Error | Order IDs should be stored as text identifiers. | None | None | Identifier format standardized in the clean table. | Data type check. | Corrected
ISS-023 | All Return Reasons | Manual entry control | Raw Returns | Return_Reason | Raw Returns -> Return_Reason | Data Entry Check | Return reasons should use controlled input. | None | None | Controlled reason selection added in the working dataset. | Standardization control. | Corrected
ISS-024 | All Returned Quantities | General format used for Returned Quantity | Raw Returns | Returned_Quantity | Raw Returns -> Returned_Quantity | Format Error | Returned Quantity should be a positive integer. | None | None | Numeric format standardized in the clean table. | Data type check. | Corrected
ISS-025 | Product_ID | One product is listed in Products but not used in Orders. | RAW_Orders | Raw Products | Raw Orders -> Raw Products | Relationship Check | A Product_ID exists in Products but is not used by Orders. | Unused product | No change | No synthetic order added; existing data preserved. | Relationship check. | Closed - No Action Required | An unused product is not necessarily a data error.
ISS-026 | Order_ID O999999 | Return Order ID not found in Orders | Raw Returns | RAW_Orders | Raw Returns -> Raw Orders | Referential Integrity | O999999 exists in Returns but not in Orders. | O999999 | No change | Return record retained; no synthetic order created. | Order ID cross-check. | Closed - No Action Required | No reliable source exists to identify the correct order.
ISS-027 | All Discount Rates | General format used for Discount Rate | RAW_Orders | Discount_Rate | Raw Orders -> Discount_Rate | Format Error | Discount Rate should use percentage formatting. | 0.15 | 0.15 | Percentage format standardized in the clean table. | Data type check. | Corrected